## Team Roles
Name | Role | Responsibilities | Status
Stefano | CEO / Founder | Vision, strategy, sales, client relationships, final decisions | Active
Mac | COO / Co-Founder | Technical execution, operations, tool setup, AI configuration, problem-solving | Active

## 2-Week Launch Plan
Day | Date Range | Task | Owner | Status
Day 1 | Week 1 | Set up GoHighLevel account & CRM pipeline | Mac
Day 1 |  | Finalize FNDI branding, website copy & pricing | Stefano
Day 2 |  | Configure Synthflow AI voice agent | Mac
Day 2 |  | Build target client list (50 local businesses) | Stefano
Day 3 |  | Connect Twilio phone number + test calls | Mac
Day 3 |  | Write outreach scripts (cold call + email) | Stefano
Day 4 |  | Set up GoHighLevel automations & follow-ups | Mac
Day 4 |  | Create demo video / screen recording | Stefano
Day 5 |  | Full end-to-end test: call → AI → CRM → follow-up | Both
Day 5 |  | Fix any bugs, polish demo flow | Mac
Day 6 | Week 2 | Start outreach — call/email first 10 businesses | Stefano
Day 6 |  | Monitor AI calls, tune responses | Mac
Day 7 |  | Follow up on Day 6 leads, book demos | Stefano
Day 7 |  | Build client onboarding checklist | Mac
Day 8 |  | Run 2-3 live demos with interested prospects | Stefano
Day 8 |  | Customize AI agent per prospect industry | Mac
Day 9 |  | Outreach to next 15 businesses | Stefano
Day 9 |  | Set up client dashboard in GoHighLevel | Mac
Day 10 |  | Close first 1-2 paying clients | Stefano
Day 10 |  | Onboard first clients, deploy their AI agents | Mac
Day 11-14 |  | Continue outreach cycle — aim for 5 clients | Stefano
Day 11-14 |  | Support live clients, gather feedback, iterate | Mac

## Tool Costs
FNDI — TOOL STACK & MONTHLY COSTS
Tool | What It Does | Plan | Monthly Cost | Priority
GoHighLevel | CRM, SMS, email, pipelines, booking | Agency Starter | 97 | 🔴 Must Have
Synthflow AI | Voice agents for phone calls | Starter | 29 | 🔴 Must Have
Twilio | Phone numbers & call routing | Pay-as-you-go | 20 | 🔴 Must Have
OpenAI API | GPT for chatbot & voice AI brain | Pay-as-you-go | 20 | 🔴 Must Have
Chatbase | Website chatbot builder | Free / Hobby | 0 | 🟡 Important
Calendly | Booking & scheduling | Free | 0 | 🟢 Already Set Up
Canva | Proposals, graphics, social media | Free | 0 | 🟢 Already Set Up
Make.com | Automation workflows | Free (1000 ops) | 0 | 🟡 Important
Zapier | Backup automation tool | Free (100 tasks) | 0 | 🟡 Nice to Have
ManyChat | Instagram DM automation | Free (up to 1000) | 0 | 🟡 Important
Gmail Workspace | Professional email | Business Starter | 7 | 🟡 Nice to Have
Vercel | Website hosting | Free (Hobby) | 0 | 🟢 Already Set Up
TOTAL MONTHLY COST (to start) |  |  | 173

## Revenue Targets
FNDI — REVENUE & PROFIT PROJECTIONS
Metric | Month 1 | Month 2 | Month 3 | Month 6 | Month 12
Clients (Starter $297) | 2 | 4 | 6 | 10 | 15
Clients (Growth $697) | 1 | 2 | 4 | 8 | 12
Clients (Dominate $997) | 0 | 1 | 2 | 4 | 6
Total Clients | 3 | 7 | 12 | 22 | 33
Monthly Recurring Revenue | 1291 | 3579 | 6564 | 12534 | 18801
Setup Fees (one-time) | 2000 | 5500 | 10000 | 19000 | 28500
Tool Costs | 173 | 173 | 173 | 173 | 173
Victor Commission (25% MRR) | 322.75 | 894.75 | 1641 | 3133.5 | 4700.25
NET MONTHLY PROFIT | 795.25 | 2511.25 | 4750 | 9227.5 | 13927.75

## Sales Tracker
Business Name | Industry | Contact Method | Status | Monthly Value | Owner

## KPIs
KPI | Week 1 Target | Week 1 Actual | Week 2 Target | Week 2 Actual
Outreach calls/emails (Stefano) | 25 |  | 40
Demos booked (Stefano) | 3 |  | 5
Demos completed | 2 |  | 4
Proposals sent | 1 |  | 3
Clients closed | 0 |  | 2
AI agents deployed (Mac) | 0 |  | 2
Monthly recurring revenue | $0 |  | $1,000+
Tool stack fully tested | Yes |  | N/A