## Launch Roadmap
FNDI LAUNCH ROADMAP
86 tasks from zero to first paying clients. Mark status as you go.
# | ☐ | Task | Owner | Details | Time | Priority | Status
▶ PHASE 1: LEGAL & BUSINESS SETUP
1 | ☐ | Register LLC | CEO | Sunbiz.org (FL) or your state site. File as LLC. Cost ~$125. Save confirmation doc. | 1 day | HIGH
2 | ☐ | Get EIN number | CEO | IRS.gov > Apply for EIN online. Free, takes 5 min. Need for bank + taxes. | 30 min | HIGH
3 | ☐ | Open business bank account | CEO | Bring LLC docs + EIN to Chase, Mercury, or Relay. Keep business $ separate. | 1 day | HIGH
4 | ☐ | Set up Stripe for payments | CEO | stripe.com > Create account > Connect bank. Set up invoicing for clients. | 1 hour | HIGH
5 | ☐ | Get business email | CEO | Buy domain (fndi.ai). Set up Google Workspace ($6/mo) for pro email. | 1 hour | MED
6 | ☐ | Draft Terms of Service | CEO | Use Termly.io template. Cover: services, payment, cancellation, liability. | 2 hours | MED
7 | ☐ | Draft client contract template | CEO | 1-page: services, price, setup fee, cancellation policy. Use HelloSign. | 2 hours | MED
8 | ☐ | Set up bookkeeping | CEO | Sign up for Wave (free) or QuickBooks ($15/mo). Track all expenses from Day 1. | 1 hour | LOW
▶ PHASE 2: TOOL STACK SETUP
9 | ☐ | Sign up for GoHighLevel | COO | gohighlevel.com > Agency Unlimited ($97/mo). Your CRM + automation engine. | 30 min | HIGH
10 | ☐ | Brand your GHL agency | COO | Set agency name, logo, colors. This is the white-label dashboard clients see. | 2 hours | HIGH
11 | ☐ | Build CRM pipeline in GHL | COO | Stages: Lead > Demo Booked > Demo Done > Proposal > Won > Onboarding > Live. | 2 hours | HIGH
12 | ☐ | Build follow-up automations in GHL | COO | 3 sequences: post-demo-booking, post-demo, post-onboarding (Day 3, 7, 14). | 3 hours | HIGH
13 | ☐ | Sign up for Synthflow AI | COO | synthflow.ai > Agency plan ($29/mo). Your voice AI platform. | 30 min | HIGH
14 | ☐ | Sign up for Twilio | COO | twilio.com > Buy phone number ($1/mo). Choose local Miami number. | 30 min | HIGH
15 | ☐ | Connect Twilio to Synthflow | COO | Synthflow > Integrations > Add Twilio SID + Auth Token. Link phone number. | 30 min | HIGH
16 | ☐ | Sign up for OpenAI API | COO | platform.openai.com > Create account > Add payment > Get API key. Load $20. | 15 min | HIGH
17 | ☐ | Connect OpenAI to Synthflow | COO | Synthflow > Settings > LLM Provider > Add API key. Select GPT-4o. | 15 min | HIGH
18 | ☐ | Connect GHL to Synthflow | COO | Set up webhook so AI-booked appointments auto-create contacts in CRM. | 2 hours | HIGH
19 | ☐ | Verify Calendly setup | CEO | Confirm Calendly syncs with Google Calendar. Add buffer between calls. | 15 min | MED
20 | ☐ | Set up Zapier for extra automations | COO | Connect tools without native integrations. Ex: call done > Slack + Sheet. | 1 hour | LOW
▶ PHASE 3: AI AGENT DEVELOPMENT
21 | ☐ | Build DENTAL template | COO | Voice agent: greeting, booking, insurance Q&A, hours, emergency, transfer. | 4 hours | HIGH
22 | ☐ | Build RESTAURANT template | COO | Voice agent: reservations, hours, menu, specials, wait times, catering. | 4 hours | HIGH
23 | ☐ | Build MED SPA / SALON template | COO | Voice agent: services, pricing, booking, cancellation, prep instructions. | 4 hours | HIGH
24 | ☐ | Build REAL ESTATE template | COO | Voice agent: listings, showings, agent availability, lead qualification. | 4 hours | MED
25 | ☐ | Build LAW FIRM template | COO | Voice agent: practice areas, consultations, fees, intake, after-hours. | 4 hours | MED
26 | ☐ | Build AUTO SERVICES template | COO | Voice agent: booking, services, pricing, vehicle info, pickup/dropoff. | 4 hours | MED
27 | ☐ | Write master AI system prompt | COO | Base prompt all agents share: pro tone, no made-up info, transfer option, capture name/number/reason. | 2 hours | HIGH
28 | ☐ | Build Spanish-language AI variant | COO | Duplicate dental + restaurant in Spanish. Use Spanish ElevenLabs voice. | 3 hours | MED
29 | ☐ | Create AI testing checklist | COO | 20+ test scenarios per industry: basic booking, FAQ, edge cases, angry caller, wrong number, ask for human. | 2 hours | HIGH
30 | ☐ | Run full test battery on all templates | COO | Call each agent 10+ times. Test every scenario. Record issues. Fix and retest. | 1 day | HIGH
31 | ☐ | Set up call recording + logging | COO | Enable recording in Synthflow/Twilio. Auto-log to Google Sheet or GHL. | 1 hour | HIGH
32 | ☐ | Create client onboarding questionnaire | COO | Google Form: biz name, address, hours, services, pricing, FAQs, transfer #. | 1 hour | HIGH
▶ PHASE 4: WEBSITE & BRANDING
33 | ☐ | Finalize website copy | CEO | Review all text on fndi-site.vercel.app. Update pricing, descriptions, CTAs. | 2 hours | HIGH
34 | ☐ | Push latest index.html to GitHub | CEO | Upload the version with upgraded AI advisor (faqData + smartReply). | 30 min | HIGH
35 | ☐ | Push book/index.html to GitHub | CEO | Verify booking page loads correctly at fndi-site.vercel.app/book. | 30 min | HIGH
36 | ☐ | Add Google Analytics | COO | analytics.google.com > Create property > Add tracking code to index.html. | 30 min | MED
37 | ☐ | Add Meta Pixel (optional) | CEO | For future FB/IG ads. Add pixel now so it collects data from Day 1. | 30 min | LOW
38 | ☐ | Create social media accounts | CEO | IG: @fndi.ai, TikTok: @fndi.ai, LinkedIn: FNDI page. Use logo + bio. | 1 hour | MED
39 | ☐ | Record 60-second demo video | CEO | Screen record: call AI > it answers > books appointment > lead in CRM. | 2 hours | HIGH
40 | ☐ | Create first 3 social media posts | CEO | Launch post, demo video clip, problem stat post. Schedule with Buffer. | 1 hour | MED
41 | ☐ | Set up Gmail email signature | CEO | Open fndi-email-signature.html > Select all > Copy > Paste in Gmail settings. | 15 min | MED
42 | ☐ | Buy custom domain (optional) | CEO | Buy fndi.ai or getfndi.com. Connect to Vercel for pro URL. | 1 hour | LOW
▶ PHASE 5: SALES MATERIALS
43 | ☐ | Write cold call script | CEO | 30-sec: intro, AI answers calls 24/7, risk-free, ask to book 15-min demo. | 1 hour | HIGH
44 | ☐ | Write 3 cold email templates | CEO | Email 1: intro + value. Email 2: follow-up + video. Email 3: last chance. | 2 hours | HIGH
45 | ☐ | Write cold DM script | CEO | Short IG/LinkedIn message. Personalize first line to their business. | 30 min | MED
46 | ☐ | Create 1-page FNDI explainer PDF | CEO | What FNDI does, how it works (3 steps), pricing, Book a Demo CTA. | 2 hours | HIGH
47 | ☐ | Create industry-specific pitch lines | CEO | Dental: 'never miss a patient call.' Restaurant: 'never miss a reservation.' Etc. | 1 hour | HIGH
48 | ☐ | Build objection handling guide | CEO | 'Too expensive' > ROI math. 'Sounds robotic' > play demo. 'Let me think' > free trial. | 1 hour | HIGH
49 | ☐ | Create demo call script | CEO | 15 min: ask about biz (2), show problem (2), live demo (5), pricing (5), close (1). | 1 hour | HIGH
50 | ☐ | Set up live demo phone number | COO | Separate Twilio number running dental template. Use during demo calls. | 30 min | HIGH
▶ PHASE 6: SALES REP NETWORK
51 | ☐ | Create rep onboarding doc | CEO | 1-2 page PDF: what FNDI is, commission tiers, scripts, Calendly link, FAQ. | 2 hours | HIGH
52 | ☐ | Create rep commission tracker | CEO | Google Sheet: rep name, lead, business, date, demo booked, closed, package, commission, paid. | 1 hour | HIGH
53 | ☐ | Set up WhatsApp/Discord group | CEO | Name it 'FNDI Sales Team.' Rules: share wins, ask questions, no spam. | 15 min | HIGH
54 | ☐ | Create rep leaderboard template | CEO | Weekly ranking by deals closed. Top rep gets shoutout + bonus. Post Mondays. | 30 min | MED
55 | ☐ | Recruit first 20+ reps | CEO | Message friends individually. Personal messages > mass blasts. | 2 days | HIGH
56 | ☐ | Run 30-min Zoom training | CEO | What FNDI does (2), how to pitch (5), script walkthrough (5), roleplay (10), Q&A (8). Record it. | 1 hour | HIGH
57 | ☐ | Create 'Find Businesses' guide | CEO | Google Maps > search industry + city > get phone/email > add to call list. | 1 hour | MED
58 | ☐ | Set up rep payment system | CEO | Venmo, Zelle, or PayPal. Pay weekly or bi-weekly. Document the schedule. | 30 min | HIGH
59 | ☐ | Create rep agreement | CEO | 1-page: independent contractor, commission structure, confidentiality. Use HelloSign. | 1 hour | MED
60 | ☐ | Assign rep territories (optional) | CEO | Same city = assign zip codes. Different cities = full territory. | 30 min | LOW
▶ PHASE 7: GET FIRST 5 CLIENTS
61 | ☐ | Build target list of 50 businesses | CEO | Google Maps: 50 dental, restaurant, med spa, salon in your area. Get name, phone, email. | 2 hours | HIGH
62 | ☐ | Cold call first 20 businesses | CEO | Use script. Track: calls made, conversations, demos booked. Aim for 3-5 demos. | 1 day | HIGH
63 | ☐ | Cold email remaining 30 | CEO | Use templates. Send from biz email. Personalize first line. Follow up in 3 days. | 2 hours | HIGH
64 | ☐ | Run first 3 demo calls | CEO | Follow demo script. Have live AI number ready. Show CRM dashboard. Close or follow up same day. | 3 hours | HIGH
65 | ☐ | Close first paying client | CEO | Send contract via HelloSign. Collect setup fee + first month via Stripe. BIGGEST MILESTONE. | varies | HIGH
66 | ☐ | Onboard first client | COO | Questionnaire > get info > clone template > customize > connect phone > test 10 calls > go live. | 48 hours | HIGH
67 | ☐ | Client check-in: Day 1 | CEO | Call them. Listen to first AI calls together. Fix anything they don't like. | 30 min | HIGH
68 | ☐ | Client check-in: Day 3 | CEO | Review call logs. Share stats: X calls answered, X appointments booked. | 30 min | HIGH
69 | ☐ | Client check-in: Day 7 | CEO | First week review. Show ROI. Ask for testimonial. | 30 min | HIGH
70 | ☐ | Get first video testimonial | CEO | Ask happiest client for 30-sec video. Use on website + social + sales. | 15 min | HIGH
71 | ☐ | Close clients 2-5 | CEO | Use first client as proof. Reps should be bringing leads by now too. | 1-2 wks | HIGH
72 | ☐ | Onboard clients 2-5 | COO | Same process. Document improvements. Target: 24-hour onboarding by client 5. | varies | HIGH
▶ PHASE 8: SYSTEMS & SCALE PREP
73 | ☐ | Document onboarding SOP | COO | Step-by-step procedure. Every click, every setting, every test. For India team. | 3 hours | HIGH
74 | ☐ | Document AI configuration SOP | COO | How to clone template, customize, connect Twilio, test, go live. Screenshots. | 3 hours | HIGH
75 | ☐ | Create client support process | CEO | Support email, 4-hour response time, escalation path to COO for tech issues. | 1 hour | HIGH
76 | ☐ | Set up weekly client reporting | COO | Auto email to each client: calls answered, appointments, leads. Zapier + GHL. | 2 hours | MED
77 | ☐ | Build client dashboard in GHL | COO | Sub-account per client. Dashboard: calls, leads, appointments, pipeline. | 2 hours | MED
78 | ☐ | Create pricing increase plan | CEO | $500 (launch) > $750 (10 clients) > $1,000 (25) > $1,500 (50). | 30 min | MED
79 | ☐ | Post job listing for India engineer | COO | Upwork: 'AI Voice Agent Config Specialist - Remote.' $800-$1,200/mo. | 1 hour | MED
80 | ☐ | Interview + hire India engineer | COO | Interview 5-10. Test: configure a basic AI agent from template. Hire fastest. | 1 week | MED
81 | ☐ | Train India engineer on SOPs | COO | Walk through both SOPs. Shadow 2-3 setups. Then solo with review. | 3 days | MED
82 | ☐ | Set up QA review process | COO | Every AI agent reviewed before going live. COO approves first 20 clients. | 1 hour | HIGH
83 | ☐ | Create monthly financial review | CEO | End of month: revenue, expenses, commissions, profit, churn, rep performance. | 1 hour | MED
84 | ☐ | Collect + organize case studies | CEO | After 30 days per client: before/after stats, revenue impact, client quote. | ongoing | HIGH
85 | ☐ | Launch client referral program | CEO | 1 month free per referred business that signs up. Simple tracking sheet. | 1 hour | MED
86 | ☐ | Plan social media content calendar | CEO | 3 posts/week: Mon = client win, Wed = demo clip, Fri = behind-the-scenes. | 1 hour | MED
PROGRESS TRACKER
Total: | 86 | Done: | 0 | Remaining: | 86 | Progress: | 0%

## Tool Checklist
☐ | Tool | URL | Cost/mo | What It Does | Status
☐ | GoHighLevel | gohighlevel.com | $97 | CRM, automations, client pipeline, dashboards
☐ | Synthflow AI | synthflow.ai | $29 | Voice AI platform - build + deploy phone agents
☐ | Twilio | twilio.com | ~$20 | Phone numbers, call routing, SMS, recording
☐ | OpenAI API | platform.openai.com | ~$20 | GPT-4o powers AI conversation intelligence
☐ | ElevenLabs | elevenlabs.io | Included | Voice synthesis - human-sounding AI (via Synthflow)
☐ | Stripe | stripe.com | 2.9%/tx | Payment processing for setup fees + monthly
☐ | Calendly | calendly.com | Free | Demo booking link for prospects
☐ | Google Workspace | workspace.google.com | $6 | Business email, Drive, Calendar
☐ | Vercel | vercel.com | Free | Website hosting - auto-deploys from GitHub
☐ | GitHub | github.com | Free | Code repository for website files
☐ | HelloSign | hellosign.com | Free tier | E-signatures for contracts
☐ | Google Analytics | analytics.google.com | Free | Track website visitors + conversions
☐ | Wave | waveapps.com | Free | Bookkeeping - expenses, revenue, invoices
☐ | Buffer | buffer.com | Free tier | Schedule social media posts
☐ | Zapier | zapier.com | Free tier | Connect tools + automate workflows
☐ | Discord / WhatsApp | discord.com | Free | Sales rep group chat + leaderboard
☐ | Upwork | upwork.com | Free | Hire AI engineers from India
☐ | Loom | loom.com | Free | Record demos + training videos

## Weekly Timeline
☐ | Week | Key Milestones | Target Outcome | Status
☐ | Week 1 | Register LLC, bank account, sign up for all tools, connect integrations | All tools live and connected
☐ | Week 2 | Build 3 AI templates, finalize website, create sales materials, record demo | AI agents working, sales kit ready
☐ | Week 3 | Recruit 20+ reps, run training, build target list, start outreach, first demos | Demos booked, reps activated
☐ | Week 4 | Close first 1-3 clients, onboard them, get first testimonial | First paying clients LIVE
☐ | Week 5 | Close clients 4-5, document SOPs, post first case study | 5 clients, systems documented
☐ | Week 6 | Hit 8-10 clients, post India engineer job, launch referral program | Scaling infrastructure ready
☐ | Week 7-8 | Hire + train India engineer, reps hitting stride | 15+ clients, tech team growing
☐ | Month 3 | 25-30 clients, 2nd engineer, setup fee at $1,000 | $12K-$15K MRR
☐ | Month 4-6 | 50-80 clients, 3 engineers, multiple cities, inbound leads | $25K-$40K MRR
☐ | Month 7-12 | 100-200 clients, India team lead, start own AI platform | $50K-$100K MRR